## Sprint01_0805_1205
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 01 FROM 08/05 TO 12/05
No. | Task description | Type | Assign To | Status | Estimate | 08/05 | 09/05 | 10/05 | 11/05 | 12/05 | End
1 | Prototype for Assessment Page | Design
2 | +Tab List | Design | Tan | Done | 18 | 18 | 10 | 5 | 2 | 0 | 0
3 | +Tab Week | Design | Tan | Done | 18 | 18 | 10 | 5 | 2 | 0 | 0
4 | +Tab Day | Design | Tan | Done | 18 | 18 | 10 | 5 | 2 | 0 | 0
5 | Prototype for Test Page | Design
6 | +Statistic Tests | Design | Tu | Done | 18 | 15 | 10 | 5 | 2 | 0 | 0
7 | +New Tests | Design | Tu | Done | 24 | 20 | 15 | 10 | 5 | 0 | 0
8 | +Assignment Tests | Design | Tu | Done | 12 | 8 | 5 | 3 | 0 | 0 | 0
9 | Prototype for Appointment | Design
10 | +For Student | Design | Thi | Done | 25 | 20 | 18 | 12 | 4 | 0 | 0
11 | +For Educator | Design | Thi | Done | 25 | 20 | 18 | 15 | 5 | 0 | 0
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
Total
Type | Code
Test
Design
Review
Doc
Resource
Tu
Thi
Tan
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled

## Sprint02_1305_1905
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 02 FROM 13/05 TO 19/05
No. | Task description | Type | Assign To | Status | Estimate | 13/05 | 14/05 | 15/05 | 16/05 | 17/05 | 18/05 | 19/05 | End
1 | Report 1 | Doc | TanND | Done | 15 | 12 | 11 | 9 | 4 | 0 | 0 | 0 | 0
2 | Tests & Assessment
3 | +List Recent Tests | Code | TanND | Done | 18 | 15 | 12 | 10 | 8 | 4 | 1 | 0 | 0
4 | +List Running Tests | Code | TanND | Done | 18 | 5 | 5 | 5 | 5 | 2 | 1 | 0 | 0
5 | +List Tests on Month tab | Code | TanND | In Progress | 15 | 13 | 12 | 10 | 8 | 6 | 4 | 4 | 4
6 | New Tests Page
7 | +Create tests function | Code | TuHM | In Progress | 30 | 28 | 25 | 23 | 22 | 20 | 18 | 16 | 15
8 | +Reuse tests function | Code | TuHM | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
9 | +Import tests function | Code | TuHM | In Progress | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
10 | Searching function
11 | +Search on tests page | Code | AnhAN | Done | 15 | 15 | 15 | 15 | 10 | 5 | 2 | 0 | 0
12 | +Search on student page | Code | AnhAN | Done | 15 | 15 | 15 | 15 | 8 | 6 | 3 | 0 | 0
13 | +Search on teacher page | Code | AnhAN | Done | 15 | 15 | 15 | 15 | 8 | 6 | 3 | 0 | 0
14 | Appointment function
15 | +Appointment for student | Code | ThiBT | In Progress | 15 | 15 | 15 | 15 | 13 | 12 | 12 | 12 | 12
16 | +Appointment email for student | Code | ThiBT | In Progress | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
17 | +Appointment for teacher | Code | ThiBT | In Progress | 15 | 15 | 15 | 15 | 13 | 12 | 12 | 12 | 12
18 | +Appointment email for teacher | Code | ThiBT | In Progress | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled
Note on L11: Tu Huynh: DEAD LINE

## Sprint03_2005_2605
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 03 FROM 20/05 TO 26/05
No. | Task description | Type | Assign To | Status | Estimate | 20/05 | 21/05 | 22/05 | 23/05 | 24/05 | 25/05 | 26/05 | End
1 | Report 2 - Project management plan | Doc | TanND | Done | 5 | 4 | 4 | 4 | 3 | 2 | 0 | 0 | 0
2 | Report 2 - Coding Convention | Doc | TanND | Done | 5 | 4 | 3 | 3 | 2 | 0 | 0 | 0 | 0
3 | Tests & Assessment
4 | +List Tests on Month Tab | Code | TanND | Done | 20 | 18 | 15 | 12 | 10 | 7 | 4 | 0 | 0
5 | +List Tests status on schedul/calendar | Code | TanND | Done | 20 | 18 | 15 | 10 | 8 | 5 | 3 | 0 | 0
6 | New Tests Page
7 | +Create tests function | Code | TuHM | Done | 15 | 12 | 10 | 8 | 6 | 5 | 3 | 0 | 0
8 | +Reuse tests function | Code | TuHM | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
9 | +Import tests function | Code | TuHM | In Progress | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
10 | Report 2 - Problem definition | Doc | TuHM | Done | 10 | 8 | 6 | 4 | 3 | 0 | 0 | 0 | 0
11 | Report 2 - Project organization | Doc | TuHM | Done | 10 | 8 | 6 | 3 | 2 | 0 | 0 | 0 | 0
12 | Appointment function
13 | +Appointment for student | Code | ThiBT | In Progress | 12 | 12 | 12 | 11 | 11 | 10 | 10 | 10 | 10
14 | +Appointment email for student | Code | ThiBT | In Progress | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
15 | +Appointment for teacher | Code | ThiBT | In Progress | 12 | 12 | 12 | 11 | 11 | 10 | 10 | 10 | 10
16 | +Appointment email for teacher | Code | ThiBT | In Progress | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
17 | New Tests Page
18 | +Setting Apply function | Code | ThiBT | In Progress | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
19 | New Tests Page - Invitation function
20 | +List Student & Teacher | Code | AnhAN | Done | 20 | 18 | 15 | 12 | 8 | 5 | 3 | 0 | 0
21 | +Create Invitation | Code | AnhAN | In Progress | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
22 | +Add user in Invitation | Code | AnhAN | In Progress | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
23 | +Delete user in Invitation | Code | AnhAN | In Progress | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled
Note on G14: Tu Huynh: Sprint 2
Note on G17: Tu Huynh: Sprint 2
Note on G18: Tu Huynh: Sprint 2
Note on G19: Tu Huynh: Sprint 2
Note on G23: Tu Huynh: Sprint 2
Note on G24: Tu Huynh: Sprint 2
Note on G25: Tu Huynh: Sprint 2
Note on G26: Tu Huynh: Sprint 2

## Sprint04_2705_0206
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 04 FROM 27/05 TO 02/06
No. | Task description | Type | Assign To | Status | Estimate | 27/05 | 28/05 | 29/05 | 30/05 | 31/05 | 01/06 | 02/06 | End
1 | Do Test
2 | +Do Test Layout | Code | TanND | Done | 15 | 10 | 3 | 0 | 0 | 0 | 0 | 0 | 0
3 | +Do Test Function | Code | TanND | In Progress | 40 | 40 | 40 | 35 | 28 | 25 | 24 | 22 | 22
4 | List upcoming Tests | Code | TanND | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
5 | New Tests Page
6 | +Reuse tests function | Code | TuHM | Done | 10 | 8 | 5 | 4 | 1 | 0 | 0 | 0 | 0
7 | +Import tests function | Code | TuHM | Done | 15 | 13 | 10 | 7 | 4 | 2 | 0 | 0 | 0
8 | +Setting Apply function | Code | TuHM | In Progress | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
9 | Report 3- Use Case Detail (10) | Doc | TuHM | Done | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0
10 | Report 3- User Requirement Specify | Doc | TuHM | Done | 15 | 13 | 10 | 7 | 4 | 2 | 0 | 0 | 0
11 | Appointment function
12 | +Appointment for student | Code | ThiBT | Done | 10 | 8 | 6 | 4 | 3 | 1 | 0 | 0 | 0
13 | +Appointment email for student | Code | ThiBT | In Progress | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
14 | +Appointment for teacher | Code | ThiBT | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
15 | +Appointment email for teacher | Code | ThiBT | In Progress | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
16 | +Appointment UnAssign for teacher/student | Code | ThiBT | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
17 | New Tests Page - Invitation function
18 | +Create Invitation | Code | AnhAN | In Progress | 12 | 10 | 8 | 7 | 6 | 5 | 5 | 5 | 5
19 | +Add user in Invitation | Code | AnhAN | In Progress | 12 | 10 | 8 | 7 | 6 | 4 | 2 | 0 | 0
20 | +Delete user in Invitation | Code | AnhAN | In Progress | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
21 | +Invite User outside of system | Code | AnhAN | In Progress | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled
Note on G13: Tu Huynh:May Span TWO Sprint
Note on G16: Tu Huynh: Sprint 3
Note on G17: Tu Huynh: Sprint 3
Note on G18: Tu Huynh: Sprint 3 of ThiBT
Note on G22: Tu Huynh: Sprint 3
Note on G23: Tu Huynh: Sprint 3
Note on G24: Tu Huynh: Sprint 3
Note on G25: Tu Huynh: Sprint 3
Note on G28: Tu Huynh: Sprint 3
Note on G29: Tu Huynh: Sprint 3
Note on G30: Tu Huynh: Sprint 3

## Sprint05_0306_0906
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 05 FROM 03/06 TO 09/06
No. | Task description | Type | Assign To | Status | Estimate | 03/06 | 04/06 | 05/06 | 06/06 | 07/06 | 08/06 | 09/06 | End
1 | Do Test
2 | Report 3- Use Case Detail (20) | Doc | TanND | Done | 20 | 18 | 14 | 10 | 6 | 2 | 0 | 0 | 0
3 | +Do Test Function | Code | TanND | In Progress | 22 | 18 | 16 | 15 | 11 | 15 | 5 | 5 | 5
4 | List upcoming Tests | Code | TanND | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
5 | New Tests Page
6 | +Report 3 - Use Case | Doc | TuHM | Done | 20 | 18 | 17 | 15 | 12 | 8 | 4 | 0 | 0
7 | +Report 3 - Entity diagram | Doc | TuHM | Done | 20 | 18 | 17 | 15 | 12 | 8 | 4 | 0 | 0
8 | +Setting Apply function | Code | TuHM | Done | 12 | 10 | 8 | 7 | 5 | 3 | 1 | 0 | 0
9 | Appointment function
10 | +Appointment email for student | Code | ThiBT | In Progress | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
11 | +Appointment for teacher | Code | ThiBT | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
12 | +Appointment email for teacher | Code | ThiBT | In Progress | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
13 | +Appointment UnAssign for teacher/student | Code | ThiBT | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
14 | New Tests Page - Invitation function
15 | +Create Invitation | Code | AnhAN | In Progress | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
16 | +Delete user in Invitation | Code | AnhAN | In Progress | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
17 | +Invite User outside of system | Code | AnhAN | In Progress | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled
Note on G13: Tu Huynh:May Span TWO Sprint

## Sprint06_1006_1606
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 06 FROM 10/06 TO 16/06
No. | Task description | Type | Assign To | Status | Estimate | 10/06 | 11/06 | 12/06 | 13/06 | 14/06 | 15/06 | 16/06 | End
1 | Do Test
2 | +Do Test Function | Code | TanND | Done | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0
3 | +List upcoming Tests | Code | TanND | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
4 | +Report 4 - Sequence Diagram | Doc | TanND | Done | 20 | 18 | 15 | 13 | 9 | 6 | 3 | 0 | 0
5 | +Authentication | Code | TuHM | Done | 20 | 18 | 15 | 13 | 8 | 6 | 3 | 0 | 0
6 | +Report 4 - Class diagram | Doc | TuHM | Done | 20 | 18 | 16 | 14 | 10 | 7 | 3 | 0 | 0
7 | +New Tests Page - Score Tab | Code | TuHM | In Progress | 15 | 14 | 12 | 10 | 10 | 10 | 10 | 10 | 10
8 | Appointment function
9 | +Appointment email for student | Code | ThiBT | Pending | 12
10 | +Appointment for teacher | Code | ThiBT | Done | 10 | 9 | 7 | 6 | 5 | 3 | 1 | 0 | 0
11 | +Appointment email for teacher | Code | ThiBT | Pending | 12
12 | +Appointment UnAssign for teacher/student | Code | ThiBT | Done | 10 | 9 | 7 | 6 | 5 | 3 | 1 | 0 | 0
13 | +Report 4 - User Interface Detail(7) | Doc | ThiBT | Done | 15 | 13 | 12 | 10 | 7 | 4 | 2 | 0 | 0
14 | New Tests Page - Invitation function
15 | +Report 4 - User Interface Detail(7) | Doc | AnhAN | Done | 15 | 13 | 12 | 10 | 7 | 4 | 2 | 0 | 0
16 | +Create Invitation | Code | AnhAN | Done | 5 | 5 | 4 | 2 | 1 | 0 | 0 | 0 | 0
17 | +Delete user in Invitation | Code | AnhAN | Done | 12 | 10 | 8 | 6 | 5 | 3 | 1 | 0 | 0
18 | +Invite User outside of system | Code | AnhAN | Pending | 20
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled
Note on G12: Tu Huynh:May Span TWO Sprint

## Sprint07_1706_2306
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 08 FROM 17/06 TO 23/06
No. | Task description | Type | Assign To | Status | Estimate | 17/06 | 18/06 | 19/06 | 20/06 | 21/06 | 22/06 | 23/06 | End
2 | +Apply seting on Do Test | Code | TanND | In Progress | 75 | 67 | 61 | 61 | 54 | 50 | 45 | 44 | 44
3 | +List upcoming Tests | Code | TanND | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
4 | +Role in invitation | Code | TuHM | Done | 20 | 18 | 15 | 12 | 8 | 5 | 3 | 0 | 0
| +New Tests Page - Response Tab | Code | TuHM | Done | 20 | 18 | 15 | 12 | 8 | 5 | 3 | 0 | 0
5 | +New Tests Page - Score Tab | Code | TuHM | In Progress | 20 | 18 | 16 | 14 | 13 | 10 | 8 | 7 | 7
6 | +Send mail notify users when invite | Code | AnhAN | In Progress | 25 | 23 | 20 | 18 | 15 | 12 | 10 | 10 | 10
7 | +Manage Tags | Code | AnhAN | Pending | 25
8 | +Student feedback on test | Code | ThiBT | In Progress | 25 | 24 | 23 | 22 | 20 | 20 | 20 | 20 | 20
9 | +Teacher see feedback of student | Code | ThiBT | In Progress | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled
Note on G11: Tu Huynh:May Span TWO Sprint

## Sprint08_2406_3006
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 08 FROM 24/06 TO 30/06
No. | Task description | Type | Assign To | Status | Estimate | 24/06 | 25/06 | 26/06 | 27/06 | 28/06 | 29/06 | 30/06 | End
1 | +Apply seting on Do Test | Code | TanND | In Progress | 44 | 43 | 40 | 38 | 36 | 28 | 25 | 25 | 25
2 | +List upcoming Tests | Code | TanND | In Progress | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
3 | +Manage Tags | Code | TuHM | Done | 25 | 22 | 18 | 14 | 10 | 6 | 2 | 0 | 0
4 | +New Tests Page - Score - Chart | Code | TuHM | Done | 10 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0
5 | +New Tests Page - Score Tab | Code | TuHM | Done | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0
6 | +Send mail notify users when invite | Code | AnhAN | Done | 25 | 22 | 18 | 15 | 10 | 7 | 3 | 0 | 0
7 | +Send mail notify users when re-invite | Code | AnhAN | Pending | 15 | 13 | 10 | 7 | 4 | 2 | 1 | 0 | 0
8 | +Student feedback on test | Code | ThiBT | In Progress | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
9 | +Teacher see feedback of student | Code | ThiBT | Done | 25 | 20 | 15 | 10 | 8 | 5 | 3 | 0 | 0
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled
Note on G11: Tu Huynh:May Span TWO Sprint

## Sprint09_0107_0707
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 09 FROM 01/07 TO 07/07
No. | Task description | Type | Assign To | Status | Estimate | 01/07 | 02/07 | 03/07 | 04/07 | 05/07 | 06/07 | 07/07 | End
1 | +Apply seting on Do Test | Code | TanND | In Progress | 25 | 23 | 20 | 18 | 17 | 16 | 15 | 15 | 15
2 | +Apply events on Calendar | Code | TanND | Done | 20 | 18 | 16 | 12 | 7 | 3 | 0 | 0 | 0
3 | +List upcoming Tests | Code | TanND | In Progress | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
4 | +Email to access test by token | Code | TuHM | In Progress | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
5 | +Apply start-end date on test | Code | TuHM | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
6 | +Import question by file | Code | TuHM | Done | 8 | 6 | 4 | 3 | 2 | 0 | 0 | 0 | 0
7 | +Search test by Tags | Code | TuHM | Done | 20 | 15 | 12 | 9 | 7 | 5 | 3 | 0 | 0
8 | +Asynchornous send mail | Code | AnhAN | In Progress | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
9 | +Search student in Popups of invitation tab | Code | AnhAN | In Progress | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
10 | +Student feedback on test | Code | ThiBT | In Progress | 20 | 18 | 15 | 13 | 10 | 10 | 10 | 10 | 10
11 | +Sort name/date when teacher see feedback list | Code | ThiBT | Done | 10 | 8 | 5 | 3 | 1 | 0 | 0 | 0 | 0
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled
Note on G11: Tu Huynh:May Span TWO Sprint

## Sprint10_0807_1407
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 10 FROM 08/07 TO 14/07
No. | Task description | Type | Assign To | Status | Estimate | 08/07 | 09/07 | 10/07 | 11/07 | 12/07 | 13/07 | 14/07 | End
1 | +Apply seting on Do Test | Code | TanND | In Progress | 15 | 14 | 13 | 12 | 12 | 12 | 12 | 12 | 12
2 | +List upcoming Tests | Code | TanND | Done | 20 | 18 | 15 | 12 | 11 | 7 | 4 | 0 | 0
3 | +Email to access test by token | Code | TuHM | Done | 20 | 17 | 13 | 10 | 6 | 4 | 2 | 0 | 0
4 | +Apply start-end date on test | Code | TuHM | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
5 | +Search reuse with test tags | Code | TuHM | Done | 20 | 17 | 15 | 13 | 10 | 6 | 3 | 0 | 0
6 | +Asynchornous send mail | Code | AnhAN | Done | 15 | 13 | 10 | 7 | 5 | 3 | 0 | 0 | 0
7 | +Search student in Popups of invitation tab | Code | AnhAN | Done | 15 | 13 | 10 | 7 | 6 | 5 | 4 | 0 | 0
8 | +Student feedback on test | Code | ThiBT | Done | 10 | 8 | 6 | 4 | 2 | 1 | 0 | 0 | 0
9 | +Real time feedback using Signal-R | Code | ThiBT | Done | 15 | 13 | 12 | 10 | 8 | 6 | 3 | 0 | 0
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled

## Sprint11_1507_2107
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 11 FROM 15/07 TO 21/07
No. | Task description | Type | Assign To | Status | Estimate | 15/07 | 16/07 | 17/07 | 18/07 | 19/07 | 20/07 | 21/07 | End
1 | +Apply seting on Do Test | Code | TanND | Done | 12 | 10 | 9 | 8 | 7 | 6 | 6 | 0 | 0
3 | +Report 5 Test Case | Doc | TanND | Done | 30 | 25 | 20 | 13 | 10 | 6 | 4 | 0 | 0
4 | +Apply start-end date on test | Code | TuHM | Done | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0
5 | +Test introduction | Code | TuHM | Done | 20 | 18 | 16 | 14 | 10 | 8 | 3 | 0 | 0
6 | +Student can view their history of test | Code | TuHM | Done | 5 | 5 | 5 | 5 | 3 | 2 | 0 | 0 | 0
7 | +Export score on tests | Code | TuHM | Done | 10 | 10 | 10 | 10 | 10 | 7 | 3 | 0 | 0
8 | +Export score of all test on teacher | Code | TuHM | Done | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0
9 | +Invitation outside users | Code | TuHM | Done | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | +Forgot password | Code | TuHM | Done | 10 | 8 | 6 | 7 | 3 | 0 | 0 | 0 | 0
11 | +Send mail access test by token | Code | AnhAN | Done | 15 | 18 | 16 | 14 | 10 | 6 | 3 | 0 | 0
12 | +Report 5 Test Case | Doc | AnhAN | Done | 30 | 26 | 22 | 18 | 15 | 10 | 6 | 0 | 0
13 | +Teacher feedback to Teacher | Code | ThiBT | Done | 10 | 8 | 5 | 3 | 2 | 0 | 0 | 0 | 0
14 | +Report 5 Test Case | Doc | ThiBT | Done | 30 | 26 | 22 | 18 | 15 | 10 | 6 | 0 | 0
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled

## Sprint12_2207_2807
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 12 FROM 22/07 TO 28/07
No. | Task description | Type | Assign To | Status | Estimate | 22/07 | 23/07 | 24/07 | 25/07 | 26/07 | 27/07 | 28/07 | End
3 | +Shuffle answers in question | Code | TanND | Done | 15 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0
4 | +Shuffle questions in test | Code | TanND | Done | 25 | 25 | 20 | 15 | 8 | 7 | 4 | 0 | 0
5 | +WYSIWYG editor | Code | TuHM | Done | 15 | 12 | 10 | 8 | 6 | 3 | 1 | 0 | 0
6 | +Teacher can update score of short/essay | Code | TuHM | Done | 15 | 13 | 9 | 7 | 4 | 3 | 3 | 0 | 0
7 | +Student can view their history of test | Code | TuHM | Done | 15 | 11 | 7 | 4 | 3 | 3 | 2 | 0 | 0
8 | +Search when reuse with test tag | Code | AnhAN
9 | +No duplicate test name | Code | AnhAN
10 | +Score to excel | Code | AnhAN
11 | +Client Sort of Response tab | Code | ThiBT
12 | +Client Sort of Score Tab | Code | ThiBT
13 | +Name of user must be not null | Code | ThiBT
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled

## Sprint13_2907_0408
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 13 FROM 29/07 TO 04/08
No. | Task description | Type | Assign To | Status | Estimate | 29/07 | 30/07 | 31/07 | 01/08 | 02/08 | 03/08 | 04/08 | End
1 | Duration Limit Setting | Code | TanND | Done | 10 | 8 | 7 | 4 | 1 | 0 | 0 | 0 | 0
2 | CountDown timer in do test | Code | TanND | Done | 10 | 9 | 8 | 8 | 8 | 3 | 0 | 0 | 0
3 | Progress bar in do test | Code | TanND | In Progress | 20 | 20 | 20 | 20 | 20 | 20 | 17 | 10 | 10
4 | Matching Question in New Test | Code | TuHM | Done | 13 | 11 | 8 | 6 | 5 | 4 | 2 | 0 | 0
5 | Reuse Matching Question | Code | TuHM | Done | 13 | 11 | 8 | 6 | 5 | 4 | 2 | 0 | 0
6 | Calculate Response of Matching Question | Code | TuHM | Done | 13 | 11 | 8 | 6 | 5 | 4 | 2 | 0 | 0
7 | Calculate Score of Matching Question | Code | TuHM | Done | 13 | 11 | 8 | 6 | 5 | 4 | 2 | 0 | 0
8 | Invitation, status of send email asynchronous | Code | AnhAN
9 | Switch percent,praction of score tab | Code | AnhAN
10 | Checking multiple condition when attempt do test | Code | AnhAN
11 | Delete permanently test | Code | AnhAN
12 | Search users of score,response | Code | ThiBT
13 | Image drag drop handling in new question | Code | ThiBT
14 | Import matching question | Code | ThiBT
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled

## Sprint14_0508_1108
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 14 FROM 05/08 TO 11/08
No. | Task description | Type | Assign To | Status | Estimate | 01/07 | 02/07 | 03/07 | 04/07 | 05/07 | 06/07 | 07/07 | End
1 | Progress bar in do test | Code | TanND | Done | 10 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0
2 | Test system logic | Test | TanND | In Progress | 30 | 30 | 30 | 25 | 17 | 15 | 12 | 10 | 10
4 | Multiple user creation | Code | TuHM | Done | 13 | 11 | 8 | 5 | 3 | 1 | 0 | 0
5 | Matching Question on Do test | Code | TuHM | Done | 13 | 10 | 8 | 7 | 4 | 1 | 0 | 0
6 | Test Response, Score calculated points | Test | TuHM | Done | 13 | 13 | 13 | 12 | 8 | 5 | 1 | 0
7 | Overview scores of all tests | Code | TuHM | Done | 13 | 13 | 13 | 10 | 7 | 4 | 2 | 0
8 | Tooltips | Code | AnhAN
9 | Report 6 - User manual | Code | AnhAN
10 | Test create test business logic | Test | AnhAN
11 | Report 6 - User manual | Code | ThiBT
12 | Test do test business logic | Test | ThiBT
13 | Client paging on do test | Code | ThiBT
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled