## Product Backlog
CAPSTONE PROJECT
| GROUP 7 | SOCIAL NETWORK FOR FOREIGN LANGUAGE LEARNING
PRODUCT BACKLOG
DOCUMENTATION
As a SE, I expect to have all related documents to be deliveried on time. Those documents are separated into 6 reports, include:
| REPORT NO. | DESCRIPTION | DELIVERY DATE
| 1 | Introduction | 2012.05.17
| 2 | Software Project Management Plan (SPM) | 2012.05.24
Problem Definition
Project organization
Project management plan
Coding convention
| 3 | Software Requirements Specifications (SRS) | 2012.06.03
User Requirement Specification
System Requirement Specification (Specific Requirements)
External Interface Requirements
System Features
Use Case Diagram & Use Case Specification
Software System Attributes
Entity Relationship Diagram
| 4 | Software Design Description (SDD) | 2012.06.14
Design Overview
System Architectural Design
Component Diagram
Detailed Description of Components
Sequence Diagram
User Interface Design
Database Design
| 5 | Software Test Documentation (STD) | 2012.07.19
Test Plan
Test Cases
Checklists
| 6 | Software User’s Manual (SUM) | 2012.08.18
Installation Guide
User’s Guide
| FINAL | Completed version of Report No.1 to Report No.6 – Soft copy | 2012.08.18
Completed version of Report No.1 to Report No.6 – Hard copy
IMPLEMENTATION
As Product Owner, I expect to have the CDs contain all source code and installable application at the end of project
Application must be developed and tested completely. Those feature need to be implemented:
| MODULE | DESCRIPTION | DELIVERY DATE
User Interface
| 0 | Friendly and easy to use web interface
| 1 | Prototype (Optional)
Database
| 0 | Database design document
| 1 | Implemented database with sample data to test
Web application
| 0 | Built on MVC Framework
| 1 | Basic features
Register to be a members
Login from valid account with ‘Forget password’ features
Logout from any page in application
User Profile management
View information
Update information
For administrator to
Manage category, courses, classes
Manage user account
| 2 | View and Search Function
Search/View list of classes
Search/View list of teachers
Search/View list of users
*Paging and Sort implemented
| 3 | Class content
Lesson resource
Unit quiz
Final test
Discussion forum
Specific events
| 4 | For teacher to create and manage class
Create a class
Track number of enrollment
Merge 2 classes
De-active class
Manage resource
Editor to create lesson content – include video, picture, text
Editor to create test and quiz – include grammar, listening, writing question
Import file excel to create test/quiz (Optional)
| 5 | For valid user to access class information and resource
View class information
Request teacher to accept enrollment
Access resource in class
| 6 | Test result
Student can do test/quiz and get report of their score
Teacher can mark and track testing result of student
| 7 | Community
For user to add friend with another user
For user to view list of friends enrolled in one class
For student to join in discussion forum
For teacher to make connection between 2 classes then sharing resource
| 8 | Automatically do by system
Suggest suitable classes for user
Remove expired users from classes
| Final | CDs contain all source code and installable application as final version | 2012.08.18

## Sprint3_0523_0529
CAPSTONE PROJECT
GROUP 7
SOCIAL NETWORK FOR FOREIGN LANGUAGE LEARNING
SPRINT 3 - FROM 23/5 TO 29/5
No. | Task description | Type | Assign To | Status | (W)23/5 | (Th)24/5 | (Fr)25/5 | (Sa)26/5 | (Su)27/5 | (Mo)28/5 | (Tu)29/5 | End Sprint
1 | Integration Report 2
2 | + Task List |  | YenMH | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | + Risk Assessment |  | DuongLS | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | + Risk Assessment | Review | All Team | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Design Database | Design | TrietNM | In Progress | 2.5
6 | Report 3 | Doc | All Team
7 | + User Requirement Specification |  | VienBN | In Progress | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
8 | + Software System Attributes |  | VienBN | In Progress | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
9 | + Entity Relationship Diagram |  | TrietNM | In Progress | 1
10 | + System Use Case |  | All Team | Done
11 | Overall use case |  | YenMH | Done | 1.5 | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 0
12 | Guest Feature use case |  | TrietNM | Done | 1
13 | User Feature use case |  | YenMH | Done | 1.5 | 1.5 | 1.5 | 1 | 0 | 0 | 0 | 0
14 | Student Feature use case |  | YenMH | Done | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
15 | Participant Feature use case |  | YenMH | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
16 | Teacher Feature use case |  | DuongLS | Done | 2.5 | [6 empty] | 0
17 | Administrator Feature use case |  | DuongLS | Done | 1.5 | [6 empty] | 0
18 | System Feature use case |  | TrietNM | In Progress | 1
Total |  |  |  |  | 22
Type | Code
Test
Design
Review
Doc
Resource
Yen
Vien
Triet
Duong
All Team
Status
In Progress
To Verify
Done
Pending
Canceled
Sprint 3:
Team tập trung hoàn thành Report 3. Tốc độ làm việc của team bắt đầu giảm so với sprint trước.
Cá nhân:
+ Viễn: task User Requirement và Software System Attributes. 2 task này có deadline là 4.5 ngày, nhưng qua hết sprint 3 Viễn chưa commit sản phẩm nào để team review. 2 task này được move sang sprint 4
-> Performance của Viễn trong sprint này không tốt. Viễn sẽ phải tập trung nhiều thời gian cho Project và chủ động communicate với team để báo cáo tiến độ + yêu cầu support nếu cần thiết
Performance: 40%
+ Triết: bắt đầu phần DB design, ERD và Use case
Team chưa thống nhất được phần DB nên task design + ERD của TRiết kéo dài sang sprint sau.
Performance: 80%
+ Dương: tập trung vào phần use case
Use case của Dương khá nhiều và có một số lỗi format, ngữ nghĩa -> team mất thêm thời gian để review và chỉnh sửa.
Performance: 80%
+ Yến: tập trung vào phần use case
Chưa đưa ra một template Use case cụ thể - gặp vấn đề trong việc assign và theo dõi task
Performance: 90%

## Sprint4_0530_0605
CAPSTONE PROJECT
GROUP 7
SOCIAL NETWORK FOR FOREIGN LANGUAGE LEARNING
SPRINT 5 FROM 30/5 TO 5/6
No. | Task description | Type | Assign To | Status | Percentage | (W)30/5 | (Th)31/5 | (Fr)1/6 | (Sa)2/6 | (Su)3/6 | (Mo)4/6 | (Tu)5/6 | End Sprint
1 | Report 3 | Doc
2 | User requirement | Doc | VienBN | Done |  | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
3 | System attributes | Doc | YenMH | Done |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Guest feature use case | Doc | TrietNM | Done |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | System feature use case | Doc | DuongLS | Done |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Update usecase use FU template |  | DuongLS | Done |  | 1.5 | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 0
7 | ERD | Doc | TrietNM | In Progress |  | 1.5 |  |  |  |  | 0.25 | 0.25 | 0.25
8 | Review report |  | VienBN, YenMH | Done | Vien: 40% Yen: 60% | 3 | 3 | 2.5 | 2 | 0.5 | 0 | 0 | 0
9 | Integrate report | Doc | YenMH | Done |  | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
10 | Report 4
11 | Database design | Design | TrietNM, DuongLS | To Verify | Triet: 60% Duong: 40% | 3 | [5 empty] | 0.5 | 0.5
12 | Database design | Review | YenMH |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
13 | Class diagram | Doc | DuongLS | In Progress |  | 2 | [6 empty] | 1
14 | Screen design - Demo | Design | YenMH | Done |  | 1.5 | 1.5 | 1.5 | 1 | 0 |  |  | 0
15 | Integrate sitemesh | Code | TrietNM | Done |  | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0
16 | Update sprint task list | Doc | YenMH | Done |  | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Total | [5 empty] | 22.5
Type | Code
Test
Design
Review
Doc
Resource
Yen
Vien
Triet
Duong
All Team
Status
In Progress
To Verify
Done
Pending
Canceled
Sprint 4:
Team tập trung hoàn thành Report 3, chuẩn bị cho report 4 và framework để code
Cá nhân:
+ Viễn: 2 task remain từ sprint 3 được phân chia lại. Viễn có 2 ngày để finish phần User Requirement -> hoàn thành đúng hạn
Task review report: phần review của Viễn cho văn phạm, ngữ pháp rất tốt nhưng Viễn chưa hoàn thành việc format + chỉnh sửa nội dung cho usecase. Commit sản phẩm trễ so với deadline.
Performance: 70%
+ Triết: Ngoài Tiếp tục design DB, sprint 4 Triết tập trung research để integrate Sitemesh và apply một số template để team review.
Performance: 90%
+ Dương: Review, bổ sung, chỉnh sửa use case và support Triết design DB.
Performance: 90%
+ Yến: System Attribute, review, chỉnh sửa use case và integrate report. Bắt đầu làm screen cho report 4
Performance: 90%

## Sprint5_0606_0612
CAPSTONE PROJECT
GROUP 7
SOCIAL NETWORK FOR FOREIGN LANGUAGE LEARNING
SPRINT 5 FROM 6/6 TO 12/6
No. | Task description | Type | Assign To | Status | (W)06/6 | (Th)07/6 | (Fr)08/6 | (Sa)09/6 | (Su)10/6 | (Mo)11/6 | (Tu)12/6 | End Sprint
1 | Report 4 | Doc
2 | Design overview | Doc | VienBN | Done | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
3 | System architecture design | Doc | VienBN, YenMH | Done | 1.5 | 1.5 | [5 empty] | 0.5
4 | CRD card | Doc | DuongLS, VienBN | Done | 2 | [6 empty] | 0
5 | Flow Chart | Doc | ViễnBN, TRiếtNM | In Progress | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1
6 | Sequence diagram | Doc | DuongLS, VienBN | In Progress | 4 | [6 empty] | 2
7 | User interface | Doc | YenMH | In Progress | 3 | 3 | 2 | 1 | 1 | 1 | 0 | 0
8 | Database design | Doc | TrietNM | In Progress | 2 | [6 empty] | 0
9 | Coding
10 | Login | Code | YenMH | Done | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
11 | Select languages | Code | YenMH | Done | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 0
12 | Select courses | Code | YenMH | In Progress | 2
13 | Create leson | Code | TrietNM | In Progress | 2
14 | Research Password encoding | Code | TrietNM | To Verify | 1 | [6 empty] | 0
15
Total |  |  |  |  | 22.5
Type | Code
Test
Design
Review
Doc
Resource
Yen
Vien
Triet
Duong
All Team
Status
In Progress
To Verify
Done
Pending
Canceled
Sprint 5:
Team tập trung hoàn thành Report 4 và DB, bắt đầu code một số màn hình.
Trong tuần SE0427 có 2 bài assignment liên tiếp của môn OB nên team không thể tập trung 100% vào Project. Coding một số màn hình được move sang sprint sau.
Cá nhân:
+ Viễn: Phần design overview + system architecture kéo dài -> Viễn không thể support Dương phần sequence + class diagram
Phần Flow chart chuyển sang cho TRiết
Performance: 60%
+ Triết: Triết chưa chủ động sắp xếp để join vào team meeting. Triết dành thời gian để nghiên cứu framework và research nên task report chậm.
Performance: 80%
+ Dương: Task report của Dương rất nặng, Dương phải hoàn thành CLass diagram và Sequence -> Tuy còn lỗi format UML nhưng Dương hoàn thành rất tốt + đảm bảo thời gian
Performance: 90%
+ Yến: Hoàn thành screen design và coding
Performance: 90%

## Sprint6'7'8_0625_0715
CAPSTONE PROJECT
GROUP 7
SOCIAL NETWORK FOR FOREIGN LANGUAGE LEARNING
SPRINT 6 + 7 + 8 FROM 25/6 TO 15/7
No. | Task description | Type | Assign To | Status | 25/6 | 26/6 | 27/6 | 28/6 | 29/6 | 30/6 | 1/7 | 2/7 | 3/7 | 4/7 | 5/7 | 6/7 | 7/7 | 8/7 | 9/7 | 10/7 | 11/7 | 12/7 | 13/7 | 14/7 | End
1 | Sitemesh - Master page for guest and user | Code | VienBN | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2.5 | 2 | 1 | 0
2 | Homepage | Code | VienBN | Done | 1 | 0
3 | + Learning Tab (Screen) | Code | VienBN | Done | 0.5 | 0.5 | 0
4 | + Teaching Tab (Screen) | Code | VienBN | Done | 0.5 | 0.5 | 0.5 | 0
5 | + Communication Tab (Screen) | Code | VienBN | Done | 0.5 | 0.5 | 0.5 | 0.5 | 0
6 | Integrate source code | Code | VienBN | Done | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 1 | 0
7 | Administrator screen | Code | VienBN | Canceled
8 | Apply stylesheet for | Code | VienBN
9 | + CRUD course | Code | VienBN | Pending | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
10 | + CRUD class | Code | VienBN | Pending | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
11 | + CRUD lesson | Code | VienBN | Pending | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
12 | + CRUD quiz | Code | VienBN | Pending | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
13
14 | Register screen | Code | TrietNM |  | 1
15 | + Password encoding | Code | TrietNM | Done | 1
16 | Add new course screen | Code | TrietNM | Done | 2
17 | Add new lesson screen | Code | TrietNM
18 | + Lesson information | Code | TrietNM | Done | 1
19 | + Add new lesson part into lesson | Code | TrietNM | Done | 3
20 | + Select existed lesson part in DB | Code | TrietNM | Done | 3
21 | Administrator screen | Code | TrietNM | In Progress | 2
22 | + Configure system | Code | TrietNM
23 | Activities Screen - For user | Code | TrietNM
24 | + View all enrolled classes | Code | TrietNM | Pending | 1.5
25 | + View overall report | Code | TrietNM | Pending | 2
26 | Activities Screen - For teacher | Code | TrietNM
27 | + View all created courses/classes | Code | TrietNM | Pending | 1.5
28 | + <Integrate> Create new course | Code | TrietNM | Pending | 0.25
29 | + <Integrate> Create new class | Code | TrietNM | Pending | 0.25
30
31 | Add new quiz screen | Code | DuongLS
32 | + Quiz information | Code | DuongLS | Done | 2 | 1 | 0
33 | + Add new questions to quiz | Code | DuongLS | Done | 2 | 2 | 2 | 2 | 1.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | + Add new question has resource to quiz | Code | DuongLS | In Progress | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
35 | + Add existed questions in DB to quiz | Code | DuongLS | Done | 3 | 3 | 3 | 3 | 2.5 | 2 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | Do quiz Screen | Code | DuongLS
37 | + Display all question of quiz (has paging) | Code | DuongLS | Pending | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
38 | + Time counter to open/close quiz | Code | DuongLS | Pending | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
39 | + Save user quiz to DB | Code | DuongLS | Pending | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
40 | Personal page | Code | DuongLS
41 | + View user page | Code | DuongLS | Pending | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
42 | + Friend request | Code | DuongLS | Pending | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
43
44 | Course category screen - design | Design | YenMH | Done | 1.5 | 0.5 | 0 | [17 empty] | 0
45 | + Course category information | Code | YenMH | Done | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | [11 empty] | 0
46 | + Level information | Code | YenMH | Done | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | [11 empty] | 0
47 | + Course list with course information | Code | YenMH | Done | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | [10 empty] | 0
48 | + Active classes (belong to course) | Code | YenMH | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | [9 empty] | 0
49 | + List user enrolled in class | Code | YenMH | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1.5 | 1 | 0 |  |  | 0
50 | + Placement test | Code | YenMH | Pending | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
51 | Class page - Design | Design | YenMH | Done | 1.5 | 1.5 | 1 | 0 | [16 empty] | 0
52 | Class page - Class infomation | Code | YenMH | Done | 0.5 | 0.5 | 0.5 | 0.5 | 0 | [15 empty] | 0
53 | Class page - Units - Design | Design | YenMH | Done | 1 | 1 | 1 | 1 | 0.5 | 0 | [14 empty] | 0
54 | + Lesson information | Code | YenMH | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | [5 empty] | 0
55 | + Quiz information + report of attempts | Code | YenMH | Done | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  |  |  | 0
56 | Class page - Discussion Forum - Design | Design | YenMH | Done | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 0 | [13 empty] | 0
57 | + Show list of posts/ comments in forum | Code | YenMH | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | [8 empty] | 0
58 | + Paging for posts + comments | Code | YenMH | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | [6 empty] | 0
59 | + Create new post (AJAX) | Code | YenMH | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | [7 empty] | 0
60 | + Create new comment (AJAX) | Code | YenMH | Done | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | [8 empty] | 0
61 | Class page - Recent activities - Design | Design | YenMH | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | [12 empty] | 0
62 | + Report of all quizzes and course test | Code | YenMH | In Progress | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 1 | 1
63 | + Graphic report for comparision | Code | YenMH | In Progress | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1.5 | 1.5 | 1.5
Total |  |  |  |  | 68.5
Type | Code
Test
Design
Review
Doc
Resource
Yen
Vien
Triet
Duong
All Team
Status
In Progress
To Verify
Done
Pending
Canceled
Sprint 6-7-8
Team bắt đầu tập trung effort vào coding từ sprint 6.
Thời gian đầu do mất nhiều thời gian để làm quen + integrate source code nên tốc độ code chậm và có nhiều lỗi.
Kết thúc sprint 8 team mới bắt đầu có source code Integrate hoàn chỉnh và bắt đầu code chung trên một folder source code. Nhiều màn hình bị pending -> đẩy về các sprint sau. Nguyên nhân bao gồm việc estimate thời gian không đúng, team member chưa follow vào task list, chưa tập trung effort để hoàn thành task.
Đánh giá của team (Theo thứ tự sprint 6 - 7 -8)
+ Viễn : 60% - 70% - 80%
Cần tập trung thời gian nhiều hơn - chú ý deadline để hoàn thành task của mình và không ảnh hưởng đến các task khác
+ Dương: 60% - 80% - 80%
Chú ý coding convention, communicate với team để tham khảo một số chức năng đã có sẵn -> rút ngắn thời gian code
+ Triết: 70% - 80% - 85%
Cần tập trung vào việc hoàn thành task thay vì việc research, tìm hiểu công nghệ hoặc chức năng mới
+ Yến: 80% - 90% - 90%
Cần thêm thời gian cho team management, cập nhật sprint task list, tracking công việc của team
Note on F17: Rinnie: Handover to TrietNM

## Sprint9_0716_0722
CAPSTONE PROJECT
GROUP 7
SOCIAL NETWORK FOR FOREIGN LANGUAGE LEARNING
SPRINT 9 FROM 16/7 TO 22/7
No. | Task description | Type | Assign To | Status | 16/7 | 17/7 | 18/7 | 19/7 | 20/7 | 21/7 | 22/7 | End
1 | REPORT 5 - TEST CASE | Doc | VienBN, DuongLS |  | 3.5
2 | + Select languages | Doc | VienBN |  | 0.25 | 0 | [5 empty] | 0
3 | + Course category | Doc | VienBN |  | 0.25 | 0 | [5 empty] | 0
4 | + Activities - student | Doc | VienBN |  | 0.25 | 0 | [5 empty] | 0
5 | + Class page - units | Doc | DuongLS |  | 0.25 | 0 | [5 empty] | 0
6 | + Class page - discussion forum | Doc | DuongLS |  | 0.25 | 0 | [5 empty] | 0
7 | + Class page - special topic | Doc | DuongLS |  | 0.25 | 0 | [5 empty] | 0
8 | + Class page - recent activities | Doc | DuongLS |  | 0.25 | 0 | [5 empty] | 0
9 | + Teacher : Create new lessons | Doc | VienBN |  | 0.25 | 0.25 | 0 |  |  |  |  | 0
10 | + Teacher :Create new quiz | Doc | VienBN |  | 0.25 | 0.25 | 0 |  |  |  |  | 0
11 | + Student: Do quiz | Doc | VienBN |  | 0.25 | 0.25 | 0 |  |  |  |  | 0
12 | + Student: View lesson | Doc | VienBN |  | 0.25 | 0.25 | 0 |  |  |  |  | 0
13 | + Add friend | Doc | VienBN |  | 0.25 | 0.25 | 0.25 | 0 |  |  |  | 0
14 | + <Integrate> Create report 5 | Doc | VienBN |  | 0.5 | 0.5 | 0.5 | 0 |  |  |  | 0
15
16 | PROJECT MANAGEMENT
17 | + Sprint backlog | Doc | YenMH |  | 0.5 | 0 | [5 empty] | 0
18
19 | CODING | Code | All team
20 | Activities Screen - For user
21 | + View all enrolled classes | Code | TrietNM |  | 1.5 | [6 empty] | 0
22 | + View overall report | Code | TrietNM |  | 2 | [6 empty] | 2
23 | Activities Screen - For teacher
24 | + View all created courses/classes | Code | TrietNM |  | 1.5 | [6 empty] | 0
25 | + <Integrate> Create new course | Code | TrietNM |  | 0.25 | [6 empty] | 0
26 | + <Integrate> Create new class | Code | TrietNM |  | 0.25 | [6 empty] | 0.25
27
28 | Personal page
29 | + View user page | Code | DuongLS |  | 2 | [6 empty] | 1
30 | + Friend request | Code | DuongLS |  | 1 | [6 empty] | 0.5
31 | <Integrate> Create new quiz | Code | DuongLS | Pending | 1 | [6 empty] | 1
32
33 | Class page - Recent activities
34 | + Report of all quizzes and course test | Code | YenMH |  | 1 | 1 | 1 | 1 | 1 | 0 |  | 0
35 | + Graphic report for comparision | Code | YenMH |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 0
36 | Class page - View lesson | Code | YenMH |  | 1.5 | 1.5 | 1 | 0 |  |  |  | 0
37 | Class page - Special Topic | Design | YenMH |  | 1.5 | 1.5 | 1 | 1 | 0 |  |  | 0
38 | <Integrate> Class page | Code | YenMH |  | 1 | 0 | [5 empty] | 0
39
40 | Apply stylesheet for | Code | VienBN
41 | + CRUD course | Code | VienBN |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
42 | + CRUD class | Code | VienBN |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  | 0
43 | + CRUD lesson | Code | VienBN |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  | 0
44 | + CRUD quiz | Code | VienBN |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
Total |  |  |  |  | 25.5
Type | Code
Test
Design
Review
Doc
Resource
Yen
Vien
Triet
Duong
All Team
Status
In Progress
To Verify
Done
Pending
Canceled
Sprint 9
Ngoài việc code, sprint 9 Team có task hoàn thành Test case document - Report 5
Có folder source code chung + re-estimate lại nhiều task nên sprint 9 công việc hoàn thành khoảng >80%. Team phải update sprint thường xuyên cũng như chủ động communicate để team lead + member biết được tiến độ task và các issue trong tuần
Đánh giá của Team:
+ Viễn : 80%
+ Dương: 80%
+ Triết: 85%
+ Yến: 90%

## Sprint01_0805_1205
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 01 FROM 08/05 TO 12/05
No. | Task description | Type | Assign To | Status | Estimate | 08/05 | 09/05 | 10/05 | 11/05 | 12/05 | End
1 | Prototype for Assessment Page | Design
2 | +Tab List | Design | Tan | Done | 3 | 3 | 3 | 2 | 1 | 0 | 0
3 | +Tab Week | Design | Tan | Done | 3 | 3 | 3 | 3 | 2 | 1 | 0
4 | +Tab Day | Design | Tan | Done | 3 | 3 | 3 | 3 | 2 | 1 | 0
5 | Prototype for Test Page | Design
6 | +Statistic Tests | Design | Tu | Done | 3 | 3 | 3 | 3 | 2 | 1 | 0
7 | +New Tests | Design | Tu | Done | 4 | 3 | 2 | 1 | 0 | 0 | 0
8 | +Assignment Tests | Design | Tu | Done | 2 | 2 | 2 | 2 | 2 | 1 | 0
9 | Prototype for Appointment | Design
10 | +For Student | Design | Thi | Done | 4 | 4 | 4 | 2 | 2 | 0 | 0
11 | +For Educator | Design | Thi | Done | 4 | 4 | 4 | 3 | 3 | 1 | 0
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
Total
Type | Code
Test
Design
Review
Doc
Resource
Tu
Thi
Tan
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled

## Sprint02_1305_1905
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 02 FROM 13/05 TO 19/05
No. | Task description | Type | Assign To | Status | Estimate | 13/05 | 14/05 | 15/05 | 16/05 | 17/05 | 18/05 | 19/05 | End
1 | Report 1 | Doc | TanND | In Progress | 2 | 2 | 2 | 2 | 1 | 0
2 | Tests & Assessment
3 | +List Recent Tests | Code | TanND | In Progress | 5 | 5 | 5 | 5 | 5 | 2
4 | +List Running Tests | Code | TanND | In Progress | 5 | 5 | 5 | 5 | 5 | 2
5 | +List Tests on Month tab | Code | TanND | In Progress | 4 | 4 | 4 | 4 | 4 | 3
6 | New Tests Page
7 | +Create tests function | Code | TuHM | In Progress | 6 | 6 | 6 | 6 | 5 | 2
8 | +Reuse tests function | Code | TuHM | In Progress | 4 | 4 | 4 | 4 | 4 | 4
9 | +Import tests function | Code | TuHM | In Progress | 6 | 6 | 6 | 6 | 6 | 6
10 | Searching function
11 | +Search on tests page | Code | AnhAN | In Progress | 5 | 5 | 5 | 5 | 4 | 3
12 | +Search on student page | Code | AnhAN | In Progress | 5 | 5 | 5 | 5 | 5 | 4.5
13 | +Search on teacher page | Code | AnhAN | In Progress | 5 | 5 | 5 | 5 | 5 | 4.5
14 | Appointment function
15 | +Appointment for student | Code | ThiBT | In Progress | 5 | 5 | 5 | 5 | 4.5 | 4
16 | +Appointment email for student | Code | ThiBT | In Progress | 2 | 2 | 2 | 2 | 2 | 2
17 | +Appointment for teacher | Code | ThiBT | In Progress | 5 | 5 | 5 | 5 | 4.5 | 4
18 | +Appointment email for teacher | Code | ThiBT | In Progress | 2 | 2 | 2 | 2 | 2 | 2
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled
Note on L11: Tu Huynh: DEAD LINE