## Sheet1
No. | Product Deliverables | Task | TuHM | TanND | AnhAN | ThiBT | Unit | Size
1 | Report1 - Introduction | Project Information |  | O |  |  | Hour | 1
|  | Scenario problems |  |  | O |  | Hour | 1
|  | Solutions | O |  |  |  | Hour | 1
|  | Approaches |  |  |  | O | Hour | 1
2 | Report2- Software Project Management Plan | Problem Definition | O |  |  |  | Hour | 1
|  | Project organization | O |  |  |  | Hour | 2
|  | Project management plan | O |  |  |  | Hour | 2
|  | Coding Convention |  | O |  |  | Hour | 1
3 | Report 3- Software Requirement Specification | User Requirement Specification | O |  |  |  | Hour | 2
System Requirement Specification
|  | External Interface Requirements | O |  |  |  | Hour | 0.5
Functional Requirement
|  | Register (Usecase & Usecase Specification) |  | O |  |  | Hour | 1
|  | Login (Usecase & Usecase Specification) |  | O |  |  | Hour | 1
|  | Manage personal information (Usecase & Usecase Specification) |  | O |  |  | Hour | 1
|  | View Tests on Calendar Schedule (Usecase & Usecase Specification) |  | O |  |  | Hour | 1
|  | Search Tests (Usecase & Usecase Specification) |  | O |  |  | Hour | 1
|  | View Running Tests (Usecase & Usecase Specification) |  | O |  |  | Hour | 1
|  | View recent tests (Usecase & Usecase Specification) |  | O |  |  | Hour | 1
|  | View upcoming tests (Usecase & Usecase Specification) |  | O |  |  | Hour | 1
|  | Do Tests (Usecase & Usecase Specification) |  | O |  |  | Hour | 1
|  | Create/Edit test (Usecase & Usecase Specification) |  | O |  |  | Hour | 1
|  | Import Questions (Usecase & Usecase Specification) |  | O |  |  | Hour | 1
|  | Duplicate Question (Usecase & Usecase Specification) |  | O |  |  | Hour | 1
|  | Reuse Question (Usecase & Usecase Specification) |  | O |  |  | Hour | 1
|  | Manage Question Tag (Usecase & Usecase Specification) |  | O |  |  | Hour | 1
|  | Test Setting (Usecase & Usecase Specification) |  | O |  |  | Hour | 1
|  | Invite Users Join Test (Usecase & Usecase Specification) |  | O |  |  | Hour | 1
|  | Invite Out Side Users Join Test (Usecase & Usecase Specification) |  | O |  |  | Hour | 1
|  | Remove Question (Usecase & Usecase Specification) |  | O |  |  | Hour | 1
|  | Remove Test (Usecase & Usecase Specification) |  | O |  |  | Hour | 1
|  | Duplicate Test (Usecase & Usecase Specification) |  | O |  |  | Hour | 1
|  | View Test Scores Statistic (Usecase & Usecase Specification) |  | O |  |  | Hour | 1
|  | View Test Responses (Usecase & Usecase Specification) |  | O |  |  | Hour | 1
|  | Assign Tests to User (Usecase & Usecase Specification) |  | O |  |  | Hour | 1
|  | Manage Test Tag (Usecase & Usecase Specification) |  | O |  |  | Hour | 1
|  | Auto calculate scores (Usecase & Usecase Specification) | O |  |  |  | Hour | 1
|  | Auto generate reports (Usecase & Usecase Specification) | O |  |  |  | Hour | 1
Non-functional Requirement
|  | Reliability | O |  |  |  | Hour | 0.2
|  | Availability | O |  |  |  | Hour | 0.2
|  | Security |  |  | O |  | Hour | 0.2
|  | Maintainability |  |  | O |  | Hour | 0.2
|  | Portability |  |  |  | O | Hour | 0.2
|  | Performance |  |  |  | O | Hour | 0.2
|  | Entity Relationship Diagram | O |  |  |  | Hour | 2
4 | Report 4- Software Design Description | System Architectural Design | O |  |  |  | Hour | 1
|  | Class diagram | O |  |  |  | Hour | 5
Class specification (states, behaviors)
|  | User | O |  |  |  | Hour | 0.2
|  | AuthenticationSessionModel | O |  |  |  | Hour | 0.2
|  | CommonService | O |  |  |  | Hour | 0.2
|  | ResponseTest | O |  |  |  | Hour | 0.2
|  | ScoreTests | O |  |  |  | Hour | 0.2
|  | TestsController | O |  |  |  | Hour | 0.2
|  | UsersController | O |  |  |  | Hour | 0.2
|  | AccountController | O |  |  |  | Hour | 0.2
|  | TeachersController | O |  |  |  | Hour | 0.2
|  | StudentsController | O |  |  |  | Hour | 0.2
|  | Views | O |  |  |  | Hour | 0.2
Sequence Diagram
|  | Login Sequence |  |  | O |  | Hour | 1
|  | Register Sequence |  |  |  | O | Hour | 1
|  | Search Tests Sequence | O |  |  |  | Hour | 1
|  | Create Test Sequence | O |  |  |  | Hour | 1
|  | Duplicate Test Sequence | O |  |  |  | Hour | 1
|  | Duplicate Question Sequence | O |  |  |  | Hour | 1
|  | Reuse Question Sequence | O |  |  |  | Hour | 1
|  | Import Question Sequence | O |  |  |  | Hour | 1
|  | Remve Question Sequence | O |  |  |  | Hour | 1
|  | Invitation Sequence | O |  |  |  | Hour | 1
|  | Invite User Outside Sequence | O |  |  |  | Hour | 1
Algorithms
|  | Create Test | O |  |  |  | Hour | 0.5
|  | Do Test | O |  |  |  | Hour | 0.5
|  | Invitation | O |  |  |  | Hour | 0.5
User Interface Design
|  | Login Screen |  |  | O |  | Hour | 1
|  | Homepage Screen |  |  | O |  | Hour | 1
|  | Testlist Screen |  |  | O |  | Hour | 1
|  | Tests Search Screen |  |  | O |  | Hour | 1
|  | New Tests Screen |  |  | O |  | Hour | 1
|  | Question Contents Screen |  |  | O |  | Hour | 1
|  | Score On Tests Screen |  |  | O |  | Hour | 1
|  | Response On Tests Screen |  |  |  | O | Hour | 1
|  | Test Setting Screen |  |  |  | O | Hour | 1
|  | Invite Users Join Test Screen |  |  |  | O | Hour | 1
|  | Assign Tests to Student Screen |  |  |  | O | Hour | 1
|  | Assign Tests to Teacher Screen |  |  |  | O | Hour | 1
|  | Do Test Screen |  |  |  | O | Hour | 1
|  | Database Design |  |  |  |  | Hour
|  | Diagram | O |  |  |  | Hour | 2
|  | Table Description |  |  | O |  | Hour | 2
5 | Report 5 - Software Implementation and Test Document | Introduction
|  | System Overview | O |  |  |  | Hour | 0.5
|  | Test Approach | O |  |  |  | Hour | 0.5
Test Plan
|  | Features to be tested | O |  |  |  | Hour | 0.5
|  | Features not to be tested | O |  |  |  | Hour | 0.5
|  | Testing Tools and Environment | O |  |  |  | Hour | 0.5
Test Cases on Module
|  | Module-Register | O |  |  |  | Hour | 1
|  | Module-Login | O |  |  |  | Hour | 1
|  | Module-Searching |  |  | O |  | Hour | 1
|  | Module-Manage Personal Information |  | O |  |  | Hour | 1
|  | Module-View Tests on Calendar Schedule |  | O |  |  | Hour | 1
|  | Module-Test List View |  | O |  |  | Hour | 1
|  | Module-Test Settings |  | O |  |  | Hour | 1
|  | Module-Invitation |  |  | O |  | Hour | 1
|  | Module-View Test Responses |  |  | O |  | Hour | 1
|  | Module-Test Management |  |  | O |  | Hour | 1
|  | Module-View Test Scores |  |  | O |  | Hour | 1
|  | Module-Manage Tags |  |  |  | O | Hour | 1
|  | Module-Feedbacks |  |  |  | O | Hour | 1
|  | Module-Assign Tests to User |  |  |  | O | Hour | 1
|  | Module-Do Test |  | O |  |  | Hour | 1
|  | Module-View History of Test |  |  |  | O | Hour | 1
Checklists
|  | Checklist of Validation |  |  |  |  | Hour | 0.5
|  | Submission Checklist |  |  |  |  | Hour | 0.5
6 | Report 6 - Software User's Manual | Installation Guide |  |  |  | O | Hour | 0.5
User’s Guide
|  | Register and Login |  |  | O |  | Hour | 0.5
|  | View Tests |  |  | O |  | Hour | 0.5
|  | View Test Statistic |  |  | O |  | Hour | 0.5
|  | Create Test |  |  | O |  | Hour | 0.5
|  | Invite users into test |  |  | O |  | Hour | 0.5
|  | Review Responses |  |  | O |  | Hour | 0.5
|  | Review Scores |  |  | O |  | Hour | 0.5
|  | Setting Test |  |  |  | O | Hour | 0.5
|  | Assign or Un-assign tests to Users |  |  |  | O | Hour | 0.5
|  | Feedback |  |  |  | O | Hour | 0.5
|  | Do Test |  |  |  | O | Hour | 0.5
|  | View History of Test |  |  |  | O | Hour | 0.5
|  | Search Tests |  |  |  | O | Hour | 0.5
|  | Update profile |  |  |  | O | Hour | 0.5
Notes
No. | Function Types | Function Point Size
1 | Insert, Delete, Update, Simple Search, Login, Register, simple function or simple query on one table | 1
2 | Computed functions or joined query | 2
3 | Complex functions or multiple subquery | 3
4 | Constraint process and data integrity | 4
5 | Functions with implementing algorithms | 5
Note on C2: phuong: Each row is a topic in project document. Do not have more than 15 rows in each product deliverable. Content in this template is used for reference only and it is vary in each project
Note on D2: phuong: Only one member in line, who has main repsonsibilty in this task
Note on C11: phuong: Use bold format for tasks which have sub-tasks
Note on C12: phuong: Use Indent for sub-tasks