## Sprint01_0805_1205
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 01 FROM 08/05 TO 12/05
No. | Task description | Type | Assign To | Status | Estimate | 08/05 | 09/05 | 10/05 | 11/05 | 12/05 | End
1 | Prototype for Assessment Page | Design
2 | +Tab List | Design | Tan | Done | 18 | 18 | 10 | 5 | 2 | 0 | 0
3 | +Tab Week | Design | Tan | Done | 18 | 18 | 10 | 5 | 2 | 0 | 0
4 | +Tab Day | Design | Tan | Done | 18 | 18 | 10 | 5 | 2 | 0 | 0
5 | Prototype for Test Page | Design
6 | +Statistic Tests | Design | Tu | Done | 18 | 15 | 10 | 5 | 2 | 0 | 0
7 | +New Tests | Design | Tu | Done | 24 | 20 | 15 | 10 | 5 | 0 | 0
8 | +Assignment Tests | Design | Tu | Done | 12 | 8 | 5 | 3 | 0 | 0 | 0
9 | Prototype for Appointment | Design
10 | +For Student | Design | Thi | Done | 25 | 20 | 18 | 12 | 4 | 0 | 0
11 | +For Educator | Design | Thi | Done | 25 | 20 | 18 | 15 | 5 | 0 | 0
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
Total
Type | Code
Test
Design
Review
Doc
Resource
Tu
Thi
Tan
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled

## Sprint02_1305_1905
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 02 FROM 13/05 TO 19/05
No. | Task description | Type | Assign To | Status | Estimate | 13/05 | 14/05 | 15/05 | 16/05 | 17/05 | 18/05 | 19/05 | End
1 | Report 1 | Doc | TanND | Done | 15 | 12 | 11 | 9 | 4 | 0 | 0 | 0 | 0
2 | Tests & Assessment
3 | +List Recent Tests | Code | TanND | Done | 18 | 15 | 12 | 10 | 8 | 4 | 1 | 0 | 0
4 | +List Running Tests | Code | TanND | Done | 18 | 5 | 5 | 5 | 5 | 2 | 1 | 0 | 0
5 | +List Tests on Month tab | Code | TanND | In Progress | 15 | 13 | 12 | 10 | 8 | 6 | 4 | 4 | 4
6 | New Tests Page
7 | +Create tests function | Code | TuHM | In Progress | 30 | 28 | 25 | 23 | 22 | 20 | 18 | 16 | 15
8 | +Reuse tests function | Code | TuHM | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
9 | +Import tests function | Code | TuHM | In Progress | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
10 | Searching function
11 | +Search on tests page | Code | AnhAN | Done | 15 | 15 | 15 | 15 | 10 | 5 | 2 | 0 | 0
12 | +Search on student page | Code | AnhAN | Done | 15 | 15 | 15 | 15 | 8 | 6 | 3 | 0 | 0
13 | +Search on teacher page | Code | AnhAN | Done | 15 | 15 | 15 | 15 | 8 | 6 | 3 | 0 | 0
14 | Appointment function
15 | +Appointment for student | Code | ThiBT | In Progress | 20 | 18 | 15 | 15 | 13 | 10 | 10 | 10 | 10
16 | +Appointment email for student | Code | ThiBT | In Progress | 15 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
17 | +Appointment for teacher | Code | ThiBT | In Progress | 20 | 15 | 15 | 15 | 13 | 12 | 12 | 12 | 10
18 | +Appointment email for teacher | Code | ThiBT | In Progress | 15 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled
Note on L11: Tu Huynh: DEAD LINE

## Sprint03_2005_2605
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 03 FROM 20/05 TO 26/05
No. | Task description | Type | Assign To | Status | Estimate | 20/05 | 21/05 | 22/05 | 23/05 | 24/05 | 25/05 | 26/05 | End
1 | Report 2 - Project management plan | Doc | TanND | Done | 5 | 4 | 4 | 4 | 3 | 2 | 0 | 0 | 0
2 | Report 2 - Coding Convention | Doc | TanND | Done | 5 | 4 | 3 | 3 | 2 | 0 | 0 | 0 | 0
3 | Tests & Assessment
4 | +List Tests on Month Tab | Code | TanND | Done | 20 | 18 | 15 | 12 | 10 | 7 | 4 | 0 | 0
5 | +List Tests status on schedul/calendar | Code | TanND | Done | 20 | 18 | 15 | 10 | 8 | 5 | 3 | 0 | 0
6 | New Tests Page
7 | +Create tests function | Code | TuHM | Done | 15 | 12 | 10 | 8 | 6 | 5 | 3 | 0 | 0
8 | +Reuse tests function | Code | TuHM | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
9 | +Import tests function | Code | TuHM | In Progress | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
10 | Report 2 - Problem definition | Doc | TuHM | Done | 10 | 8 | 6 | 4 | 3 | 0 | 0 | 0 | 0
11 | Report 2 - Project organization | Doc | TuHM | Done | 10 | 8 | 6 | 3 | 2 | 0 | 0 | 0 | 0
12 | Appointment function
13 | +Appointment for student | Code | ThiBT | Done | 10 | 5 | 3 | 3 | 2 | 0 | 0 | 0 | 0
14 | +Appointment email for student | Code | ThiBT | In Progress | 12 | 12 | 10 | 9 | 9 | 6 | 6 | 4 | 4
15 | +Appointment for teacher | Code | ThiBT | Done | 10 | 5 | 5 | 5 | 2 | 2 | 0 | 0 | 0
16 | +Appointment email for teacher | Code | ThiBT | In Progress | 12 | 10 | 10 | 10 | 10 | 10 | 6 | 6 | 4
17 | New Tests Page
18 | +Setting Apply function | Code | ThiBT | In Progress | 15 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 10
19 | New Tests Page - Invitation function
20 | +List Student & Teacher | Code | AnhAN | Done | 20 | 18 | 15 | 12 | 8 | 5 | 3 | 0 | 0
21 | +Create Invitation | Code | AnhAN | In Progress | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
22 | +Add user in Invitation | Code | AnhAN | In Progress | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
23 | +Delete user in Invitation | Code | AnhAN | In Progress | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled
Note on G14: Tu Huynh: Sprint 2
Note on G17: Tu Huynh: Sprint 2
Note on G18: Tu Huynh: Sprint 2
Note on G19: Tu Huynh: Sprint 2
Note on G23: Tu Huynh: Sprint 2
Note on G24: Tu Huynh: Sprint 2
Note on G25: Tu Huynh: Sprint 2
Note on G26: Tu Huynh: Sprint 2

## Sprint04_2705_0206
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 04 FROM 27/05 TO 02/06
No. | Task description | Type | Assign To | Status | Estimate | 27/05 | 28/05 | 29/05 | 30/05 | 31/05 | 01/06 | 02/06 | End
1 | Do Test
2 | +Do Test Layout | Code | TanND | Done | 15 | 10 | 3 | 0 | 0 | 0 | 0 | 0 | 0
3 | +Do Test Function | Code | TanND | In Progress | 40 | 40 | 40 | 35 | 28 | 25 | 24 | 22 | 22
4 | List upcoming Tests | Code | TanND | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
5 | New Tests Page
6 | +Reuse tests function | Code | TuHM | Done | 10 | 8 | 5 | 4 | 1 | 0 | 0 | 0 | 0
7 | +Import tests function | Code | TuHM | Done | 15 | 13 | 10 | 7 | 4 | 2 | 0 | 0 | 0
8 | +Setting Apply function | Code | TuHM | In Progress | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
9 | Report 3- Use Case Detail (10) | Doc | TuHM | Done | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0
10 | Report 3- User Requirement Specify | Doc | TuHM | Done | 15 | 13 | 10 | 7 | 4 | 2 | 0 | 0 | 0
11 | Appointment function
12 | +Appointment email for student | Code | ThiBT | Done | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0
13 | +Appointment email for teacher | Code | ThiBT | Done | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0
14 | +Appointment UnAssign for teacher/student | Code | ThiBT | In Progress | 20 | 18 | 15 | 13 | 13 | 10 | 10 | 10 | 10
15 | New Tests Page - Invitation function
16 | +Create Invitation | Code | AnhAN | In Progress | 12 | 10 | 8 | 7 | 6 | 5 | 5 | 5 | 5
17 | +Add user in Invitation | Code | AnhAN | In Progress | 12 | 10 | 8 | 7 | 6 | 4 | 2 | 0 | 0
18 | +Delete user in Invitation | Code | AnhAN | In Progress | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
19 | +Invite User outside of system | Code | AnhAN | In Progress | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled
Note on G13: Tu Huynh:May Span TWO Sprint
Note on G16: Tu Huynh: Sprint 3
Note on G17: Tu Huynh: Sprint 3
Note on G18: Tu Huynh: Sprint 3 of ThiBT
Note on G22: Tu Huynh: Sprint 3
Note on G23: Tu Huynh: Sprint 3
Note on G26: Tu Huynh: Sprint 3
Note on G27: Tu Huynh: Sprint 3
Note on G28: Tu Huynh: Sprint 3

## Sprint05_0306_0906
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 05 FROM 03/06 TO 09/06
No. | Task description | Type | Assign To | Status | Estimate | 03/06 | 04/06 | 05/06 | 06/06 | 07/06 | 08/06 | 09/06 | End
1 | Do Test
2 | Report 3- Use Case Detail (20) | Doc | TanND | Done | 20 | 18 | 14 | 10 | 6 | 2 | 0 | 0 | 0
3 | +Do Test Function | Code | TanND | In Progress | 22 | 18 | 16 | 15 | 11 | 15 | 5 | 5 | 5
4 | List upcoming Tests | Code | TanND | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
5 | New Tests Page
6 | +Report 3 - Use Case | Doc | TuHM | Done | 20 | 18 | 17 | 15 | 12 | 8 | 4 | 0 | 0
7 | +Report 3 - Entity diagram | Doc | TuHM | Done | 20 | 18 | 17 | 15 | 12 | 8 | 4 | 0 | 0
8 | +Setting Apply function | Code | TuHM | Done | 12 | 10 | 8 | 7 | 5 | 3 | 1 | 0 | 0
9 | FeedBack
10 | +Student feedback on test | Code | ThiBT | In Progress | 25 | 24 | 23 | 22 | 20 | 20 | 20 | 15 | 15
11 | +Teacher see feedback of student | Code | ThiBT | In Progress | 25 | 24 | 23 | 22 | 20 | 20 | 15 | 15 | 15
12 | +Appointment UnAssign for teacher/student | Code | ThiBT | Done | 10 | 8 | 8 | 5 | 5 | 0 | 0 | 0 | 0
13 | New Tests Page - Invitation function
14 | +Create Invitation | Code | AnhAN | In Progress | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
15 | +Delete user in Invitation | Code | AnhAN | In Progress | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
16 | +Invite User outside of system | Code | AnhAN | In Progress | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled
Note on G13: Tu Huynh:May Span TWO Sprint

## Sprint06_1006_1606
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 06 FROM 10/06 TO 16/06
No. | Task description | Type | Assign To | Status | Estimate | 10/06 | 11/06 | 12/06 | 13/06 | 14/06 | 15/06 | 16/06 | End
1 | Do Test
2 | +Do Test Function | Code | TanND | Done | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0
3 | +List upcoming Tests | Code | TanND | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
4 | +Report 4 - Sequence Diagram | Doc | TanND | Done | 20 | 18 | 15 | 13 | 9 | 6 | 3 | 0 | 0
5 | +Authentication | Code | TuHM | Done | 20 | 18 | 15 | 13 | 8 | 6 | 3 | 0 | 0
6 | +Report 4 - Class diagram | Doc | TuHM | Done | 20 | 18 | 16 | 14 | 10 | 7 | 3 | 0 | 0
7 | +New Tests Page - Score Tab | Code | TuHM | In Progress | 15 | 14 | 12 | 10 | 10 | 10 | 10 | 10 | 10
8 | FeedBack
9 | +Student feedback on test | Code | ThiBT | In Progress | 15 | 15 | 10 | 10 | 9 | 8 | 8 | 7 | 7
10 | +Teacher see feedback of student | Code | ThiBT | Done | 15 | 10 | 5 | 5 | 5 | 3 | 0 | 0 | 0
11 | New Tests Page - Invitation function
12 | +Report 4 - User Interface Detail(7) | Doc | AnhAN | Done | 15 | 13 | 12 | 10 | 7 | 4 | 2 | 0 | 0
13 | +Create Invitation | Code | AnhAN | Done | 5 | 5 | 4 | 2 | 1 | 0 | 0 | 0 | 0
14 | +Delete user in Invitation | Code | AnhAN | Done | 12 | 10 | 8 | 6 | 5 | 3 | 1 | 0 | 0
15 | +Invite User outside of system | Code | AnhAN | Pending | 20
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled
Note on G12: Tu Huynh:May Span TWO Sprint

## Sprint07_1706_2306
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 08 FROM 17/06 TO 23/06
No. | Task description | Type | Assign To | Status | Estimate | 17/06 | 18/06 | 19/06 | 20/06 | 21/06 | 22/06 | 23/06 | End
2 | +Apply seting on Do Test | Code | TanND | In Progress | 75 | 67 | 61 | 61 | 54 | 50 | 45 | 44 | 44
3 | +List upcoming Tests | Code | TanND | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
4 | +Role in invitation | Code | TuHM | Done | 20 | 18 | 15 | 12 | 8 | 5 | 3 | 0 | 0
5 | +New Tests Page - Response Tab | Code | TuHM | Done | 20 | 18 | 15 | 12 | 8 | 5 | 3 | 0 | 0
6 | +New Tests Page - Score Tab | Code | TuHM | In Progress | 20 | 18 | 16 | 14 | 13 | 10 | 8 | 7 | 7
7 | +Send mail notify users when invite | Code | AnhAN | In Progress | 25 | 23 | 20 | 18 | 15 | 12 | 10 | 10 | 10
8 | +Manage Tags | Code | AnhAN | Pending | 25
9 | +Sort name/date when teacher see feedback list | Code | ThiBT | In Progress | 15 | 14 | 10 | 10 | 10 | 7 | 6 | 5 | 5
10 | +Student feedback on test | Code | ThiBT | Done | 7 | 6 | 6 | 3 | 2 | 0 | 0 | 0 | 0
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled
Note on G11: Tu Huynh:May Span TWO Sprint

## Sprint08_2406_3006
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 08 FROM 24/06 TO 30/06
No. | Task description | Type | Assign To | Status | Estimate | 24/06 | 25/06 | 26/06 | 27/06 | 28/06 | 29/06 | 30/06 | End
1 | +Apply seting on Do Test | Code | TanND | In Progress | 44 | 43 | 40 | 38 | 36 | 28 | 25 | 25 | 25
2 | +List upcoming Tests | Code | TanND | In Progress | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
3 | +Manage Tags | Code | TuHM | Done | 25 | 22 | 18 | 14 | 10 | 6 | 2 | 0 | 0
4 | +New Tests Page - Score - Chart | Code | TuHM | Done | 10 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0
5 | +New Tests Page - Score Tab | Code | TuHM | Done | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0
6 | +Send mail notify users when invite | Code | AnhAN | Done | 25 | 22 | 18 | 15 | 10 | 7 | 3 | 0 | 0
7 | +Send mail notify users when re-invite | Code | AnhAN | Pending | 15 | 13 | 10 | 7 | 4 | 2 | 1 | 0 | 0
8 | +Sort name/date when teacher see feedback list | Code | ThiBT | Done | 5 | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0
9 | +Teacher see feedback of student | Code | ThiBT | Done | 15 | 14 | 13 | 10 | 8 | 5 | 3 | 0 | 0
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled
Note on G11: Tu Huynh:May Span TWO Sprint

## Sprint09_0107_0707
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 09 FROM 01/07 TO 07/07
No. | Task description | Type | Assign To | Status | Estimate | 01/07 | 02/07 | 03/07 | 04/07 | 05/07 | 06/07 | 07/07 | End
1 | +Apply seting on Do Test | Code | TanND | In Progress | 25 | 23 | 20 | 18 | 17 | 16 | 15 | 15 | 15
2 | +Apply events on Calendar | Code | TanND | Done | 20 | 18 | 16 | 12 | 7 | 3 | 0 | 0 | 0
3 | +List upcoming Tests | Code | TanND | In Progress | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
4 | +Email to access test by token | Code | TuHM | In Progress | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
5 | +Apply start-end date on test | Code | TuHM | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
6 | +Import question by file | Code | TuHM | Done | 8 | 6 | 4 | 3 | 2 | 0 | 0 | 0 | 0
7 | +Search test by Tags | Code | TuHM | Done | 20 | 15 | 12 | 9 | 7 | 5 | 3 | 0 | 0
8 | +Asynchornous send mail | Code | AnhAN | In Progress | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
9 | +Search student in Popups of invitation tab | Code | AnhAN | In Progress | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
10 | +Real time feedback using Signal-R | Code | ThiBT | Done | 20 | 13 | 12 | 10 | 8 | 6 | 3 | 0 | 0
11 | +Teacher feedback to Teacher | Code | ThiBT | Done | 15 | 10 | 5 | 9 | 9 | 8 | 6 | 4 | 0
12 | Image drag drop handling in new question | Code | ThiBT | In Progress | 25 | 23 | 20 | 18 | 17 | 16 | 15 | 15 | 15
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled
Note on G11: Tu Huynh:May Span TWO Sprint

## Sprint10_0807_1407
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 10 FROM 08/07 TO 14/07
No. | Task description | Type | Assign To | Status | Estimate | 08/07 | 09/07 | 10/07 | 11/07 | 12/07 | 13/07 | 14/07 | End
1 | +Apply seting on Do Test | Code | TanND | In Progress | 15 | 14 | 13 | 12 | 12 | 12 | 12 | 12 | 12
2 | +List upcoming Tests | Code | TanND | Done | 20 | 18 | 15 | 12 | 11 | 7 | 4 | 0 | 0
3 | +Email to access test by token | Code | TuHM | Done | 20 | 17 | 13 | 10 | 6 | 4 | 2 | 0 | 0
4 | +Apply start-end date on test | Code | TuHM | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
5 | +Search reuse with test tags | Code | TuHM | Done | 20 | 17 | 15 | 13 | 10 | 6 | 3 | 0 | 0
6 | +Asynchornous send mail | Code | AnhAN | Done | 15 | 13 | 10 | 7 | 5 | 3 | 0 | 0 | 0
7 | +Search student in Popups of invitation tab | Code | AnhAN | Done | 15 | 13 | 10 | 7 | 6 | 5 | 4 | 0 | 0
8 | Search users of score,response | Code | ThiBT | In Progress | 20 | 17 | 16 | 15 | 11 | 9 | 9 | 9 | 9
9 | Image drag drop handling in new question | Code | ThiBT | Done | 15 | 13 | 12 | 10 | 17 | 12 | 8 | 5 | 0
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled

## Sprint11_1507_2107
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 11 FROM 15/07 TO 21/07
No. | Task description | Type | Assign To | Status | Estimate | 15/07 | 16/07 | 17/07 | 18/07 | 19/07 | 20/07 | 21/07 | End
1 | +Apply seting on Do Test | Code | TanND | Done | 12 | 10 | 9 | 8 | 7 | 6 | 6 | 0 | 0
3 | +Report 5 Test Case | Doc | TanND | Done | 30 | 25 | 20 | 13 | 10 | 6 | 4 | 0 | 0
4 | +Apply start-end date on test | Code | TuHM | Done | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0
5 | +Test introduction | Code | TuHM | Done | 20 | 18 | 16 | 14 | 10 | 8 | 3 | 0 | 0
6 | +Student can view their history of test | Code | TuHM | Done | 5 | 5 | 5 | 5 | 3 | 2 | 0 | 0 | 0
7 | +Export score on tests | Code | TuHM | Done | 10 | 10 | 10 | 10 | 10 | 7 | 3 | 0 | 0
8 | +Export score of all test on teacher | Code | TuHM | Done | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0
9 | +Invitation outside users | Code | TuHM | Done | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | +Forgot password | Code | TuHM | Done | 10 | 8 | 6 | 7 | 3 | 0 | 0 | 0 | 0
11 | +Send mail access test by token | Code | AnhAN | Done | 15 | 18 | 16 | 14 | 10 | 6 | 3 | 0 | 0
12 | +Report 5 Test Case | Doc | AnhAN | Done | 30 | 26 | 22 | 18 | 15 | 10 | 6 | 0 | 0
13 | Search users of score,response | Code | ThiBT | Done | 9 | 8 | 7 | 5 | 4 | 3 | 2 | 0 | 0
14 | +Report 5 Test Case | Doc | ThiBT | Done | 30 | 26 | 22 | 18 | 15 | 10 | 6 | 0 | 0
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled

## Sprint12_2207_2807
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 12 FROM 22/07 TO 28/07
No. | Task description | Type | Assign To | Status | Estimate | 22/07 | 23/07 | 24/07 | 25/07 | 26/07 | 27/07 | 28/07 | End
3 | +Shuffle answers in question | Code | TanND | Done | 15 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0
4 | +Shuffle questions in test | Code | TanND | Done | 25 | 25 | 20 | 15 | 8 | 7 | 4 | 0 | 0
5 | +WYSIWYG editor | Code | TuHM | Done | 15 | 12 | 10 | 8 | 6 | 3 | 1 | 0 | 0
6 | +Teacher can update score of short/essay | Code | TuHM | Done | 15 | 13 | 9 | 7 | 4 | 3 | 3 | 0 | 0
7 | +Student can view their history of test | Code | TuHM | Done | 15 | 11 | 7 | 4 | 3 | 3 | 2 | 0 | 0
8 | +Search when reuse with test tag | Code | AnhAN | Done | 12 | 9 | 7 | 4 | 1 | 0 | 0 | 0 | 0
9 | +No duplicate test name | Code | AnhAN | Done | 15 | 13 | 8 | 4 | 2 | 2 | 0 | 0 | 0
10 | +Score to excel | Code | AnhAN | Done | 15 | 15 | 13 | 11 | 7 | 4 | 3 | 0 | 0
11 | +Client Sort of Response tab | Code | ThiBT | Done | 10 | 9 | 8 | 8 | 7 | 6 | 3 | 0 | 0
12 | +Client Sort of Score Tab | Code | ThiBT | Done | 10 | 9 | 8 | 8 | 8 | 8 | 8 | 0 | 0
13 | +Name of user must be not null | Code | ThiBT | Done | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled

## Sprint13_2907_0408
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 13 FROM 29/07 TO 04/08
No. | Task description | Type | Assign To | Status | Estimate | 29/07 | 30/07 | 31/07 | 01/08 | 02/08 | 03/08 | 04/08 | End
1 | Duration Limit Setting | Code | TanND | Done | 10 | 8 | 7 | 4 | 1 | 0 | 0 | 0 | 0
2 | CountDown timer in do test | Code | TanND | Done | 10 | 9 | 8 | 8 | 8 | 3 | 0 | 0 | 0
3 | Progress bar in do test | Code | TanND | In Progress | 20 | 20 | 20 | 20 | 20 | 20 | 17 | 10 | 10
4 | Matching Question in New Test | Code | TuHM | Done | 13 | 11 | 8 | 6 | 5 | 4 | 2 | 0 | 0
5 | Reuse Matching Question | Code | TuHM | Done | 13 | 11 | 8 | 6 | 5 | 4 | 2 | 0 | 0
6 | Calculate Response of Matching Question | Code | TuHM | Done | 13 | 11 | 8 | 6 | 5 | 4 | 2 | 0 | 0
7 | Calculate Score of Matching Question | Code | TuHM | Done | 13 | 11 | 8 | 6 | 5 | 4 | 2 | 0 | 0
8 | Invitation, status of send email asynchronous | Code | AnhAN | Done | 12 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0
9 | Switch percent,praction of score tab | Code | AnhAN | Done | 15 | 13 | 13 | 10 | 7 | 4 | 1 | 0 | 0
10 | Checking multiple condition when attempt do test | Code | AnhAN | Done | 18 | 18 | 18 | 16 | 13 | 9 | 6 | 4 | 0
11 | Delete permanently test | Code | AnhAN | Done | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Import matching question | Code | ThiBT | Done | 15 | 13 | 10 | 8 | 7 | 5 | 4 | 2 | 0
13 | Client paging on do test | Code | ThiBT | Done | 12 | 10 | 7 | 6 | 5 | 4 | 2 | 1 | 0
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled

## Sprint14_0508_1108
CAPSTONE PROJECT
GROUP 6
Online Assessment And Testing System
SPRINT 14 FROM 05/08 TO 11/08
No. | Task description | Type | Assign To | Status | Estimate | 01/07 | 02/07 | 03/07 | 04/07 | 05/07 | 06/07 | 07/07 | End
1 | Progress bar in do test | Code | TanND | Done | 10 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0
2 | Test system logic | Test | TanND | In Progress | 30 | 30 | 30 | 25 | 17 | 15 | 12 | 10 | 10
4 | Multiple user creation | Code | TuHM | Done | 13 | 11 | 8 | 5 | 3 | 1 | 0 | 0 | 0
5 | Matching Question on Do test | Code | TuHM | Done | 13 | 10 | 8 | 7 | 4 | 1 | 0 | 0 | 0
6 | Test Response, Score calculated points | Test | TuHM | Done | 13 | 13 | 13 | 12 | 8 | 5 | 1 | 0 | 0
7 | Overview scores of all tests | Code | TuHM | Done | 13 | 13 | 13 | 10 | 7 | 4 | 2 | 0 | 0
8 | Tooltips | Code | AnhAN | Done | 20 | 16 | 13 | 10 | 6 | 4 | 2 | 0 | 0
9 | Report 6 - User manual | Code | AnhAN | Done | 18 | 15 | 13 | 8 | 5 | 2 | 1 | 0 | 0
10 | Test create test business logic | Test | AnhAN | In Progress | 25 | 21 | 19 | 17 | 16 | 13 | 10 | 7 | 7
11 | Report 6 - User manual | Code | ThiBT | Done | 10 | 7 | 5 | 3 | 2 | 1 | 0 | 0 | 0
12 | Test do test business logic | Test | ThiBT | Done | 10 | 9 | 6 | 5 | 5 | 1 | 1 | 0 | 0
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
Total
Type | Code
Test
Design
Review
Doc
Resource
TuHM
ThiBT
TanND
AnhAN
All Team
Status
New
In Progress
To Verify
Done
Pending
Canceled